## Sheet1
My Skype id : live:.cid.a3e05258f0b595aa or liz.hrglobal@gmail.com
Planning of Concern and Development Plan of Box Selling
Web APP with seller and buyers for selling boxes. |  | Activity | Progress |  | Status of Budget(k)
| Full Design | Reviewing of Details and Making Sketch |  | 2days | 7.5k
|  | www.figma.com design work |  | 7days
| Backend development with laravel | Development of API using laravel restful api under the support of Apache or linux vps server |  | 12days
| Front end Development using Vue.js | Appliance of figma design & blade grammar |  | 7days
| Integrating API | Confirming for API With Response |  | 4days
|  | Integration of front-end with API |  | 4days
| Testing | Unit testing |  | 3 Days | 1k
Integration testing
| Feedback work from client | Feedback work from client |  | 2-3days | 0.5k
|  |  |  | total 40days | 9k
|  |  |  | Bonus | 0.5k
Api what I want to get from you |  | Paypal Sandbox Api
Email Smtp Api
Aws or other Hetzner Vps or other Cpanel
Domain
You create github private two repo for laravel backend and front end vue.js repo
Additional things will be done as Free and providing maintenance for 2months as free. |  | Unlimited Revision will be provided for your project.